## Combined
S.No | Work Number | Project Name | Project Description | Administrative Sanction Date | Technical Year Sanction Date | Estimated Cost INR (Crores) | Estimated Cost USD (Millions) | Estimated Cost ₹ (Crores) | Procurement Category (Goods/Works/NCS/CS) | Procurement Method (Open/Limited/Direct) | Item Rate/Lumpsum (EPC/DBO) | Planned Issuance of NIT (month/year) | Technical Envelope Opening (Tender/RFP) | Expected Date of Contract Award [APP] | Tender Publish Date | LOA Issue | Agreement Date | Contractor | Procurement Cycle Time (NIT to Agreement) (Days) | Financial Quote (+/-) | Avg. No. of Bidders
1 | WIN/0081/25-26 | E9 Road | Arterial Road E9 | 20-12-2024 | 07.01.2025 | 583.34 | 69.45 | 583.34 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 109 | 3.84 | 3
2 | WIN/0070/25-26 | N12 Road | Arterial Road N12 | 20-12-2024 | 07.01.2025 | 614.56 | 73.16 | 614.56 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 109 | 3.94 | 3
3 | WIN/0074/25-26 | N15 Road | Arterial Road N15 | 2024-10-12 | 02.01.2025 | 482.01 | 57.38 | 482.01 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 114 | 3.32 | 3
4 | WIN/0010/24-25 | Zone-1A | LPS Zone - 1A | 2024-10-12 | 26-12-2024 | 448.32 | 53.37 | 448.32 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 117 | 3.96 | 3
5 | WIN/0011/24-25 | Zone-1B | LPS Zone - 1B | 2024-10-12 | 26-12-2024 | 588.04 | 70 | 588.04 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 117 | 4.04 | 3
6 | WIN/0014/24-25 | Zone-2A | LPS Zone - 2A | 2024-10-12 | 26-12-2024 | 542.84 | 64.62 | 542.84 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.19 | 3
7 | WIN/0016/24-25 | Zone-2B | LPS Zone - 2B | 2024-10-12 | 26-12-2024 | 542.84 | 64.62 | 542.84 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.19 | 3
8 | WIN/0008/24-25 | Zone-3A | LPS Zone - 3A | 20-12-2024 | 28-12-2024 | 505.53 | 60.18 | 505.53 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 4.24 | 3
9 | WIN/0009/24-25 | Zone-3B | LPS Zone - 3B | 20-12-2024 | 28-12-2024 | 420.65 | 50.08 | 420.65 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 114 | 3.96 | 3
10 | WIN/0023/24-25 | Zone-5B | LPS Zone - 5B | 2024-10-12 | 26-12-2024 | 603.14 | 71.8 | 603.14 | Works | Open | Lumpsum | 'Dec/2025 | 'Feb/2025 | 'Mar/2025 | 31-12-2024 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 118 | 3.77 | 3
11 | WIN/0025/24-25 | Zone-5D | LPS Zone - 5D | 2024-10-12 | 26-12-2024 | 603.65 | 71.86 | 603.65 | Works | Open | Lumpsum | 'Dec/2024 | 'Feb/2025 | 'Mar/2025 | 31-12-2024 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 118 | 4.12 | 3
12 | WIN/0021/24-25 | Zone-6 | LPS Zone - 6 | 2024-10-12 | 26-12-2024 | 530.83 | 63.19 | 530.83 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 116 | 3.64 | 3
13 | WIN/0147/25-26 | GOs and Group D employees - Housing | Multistorey apartment for GO TY-1 & TY-2 and Group D Employees | 2024-10-12 | 20.02.2025 | 594.54 | 70.78 | 594.54 | Works | Open | Lumpsum | 'Mar/2025 | 'Apr/2025 | 'May/2025 | 24-03-2025 | 14-05-2025 | 2025-04-08 | M/s. Shapoorji & Pallonji Co Ltd​ | 134 | 4.39 | 3
14 | WIN/0032/24-25 | Hon'ble MLAs and MLCs and AIS Officers - Housing | Multistorey apartment for MLA & AIS including External Infra works | 16-10-2024 | 01.01.2025 | 524.7 | 62.46 | 524.7 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 117 | 4.1 | 3
15 | WIN/0146/25-26 | NGO (Housing+Ext. Infra) - 9 Towers | Multistorey apartment for NGO Phase - 1B including External Infra works (for 9 towers) | 2024-10-12 | 20.02.2025 | 594.36 | 70.76 | 594.36 | Works | Open | Lumpsum | 'Mar/2025 | 'Apr/2025 | 'May/2025 | 24-03-2025 | 14-05-2\ | 14-07-2025 | M/s Larsen & Toubro Limited | 112 | 4.4 | 3
16 | WIN/0145/25-26 | NGO (Housing+Ext. Infra) - 12 Towers | Multistorey apartment for NGO Phase-1A including External Infra works (for 12 towers) | 2024-10-12 | 20.02.2025 | 607.5 | 72.32 | 607.5 | Works | Open | Lumpsum | 'Mar/2025 | 'Apr/2025 | 'May/2025 | 24-03-2025 | 14-05-2025 | 14-07-2025 | M/s Larsen & Toubro Limited | 112 | 4.41 | 3
17 | WIN/0034/24-25 | GOs and Group D employees - External Infra | Multistorey Apartments for GO TY-1, GO TY-II & Group - D - Phase-II (External Infrastructure) | 2024-10-12 | 20.02.2025 | 226.26 | 26.94 | 226.26 | Works | Open | Lumpsum | 'Mar/2025 | 'Apr/2025 | 'May/2025 | 24-03-2025 | 14-05-2025 | 14-07-2025 | M/s. Shapoorji & Pallonji Co Ltd​ | 112 | 4.39 | 3
18 | WIN/0086/25-26 | N6 Utilities | N6 - Utilities only | 20-12-2024 | 07.01.2025 | 232.86 | 27.72 | 232.86 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 109 | 4.02 | 3
19 | WIN/0077/25-26 | Flood Works - Neerukonda Reservoir | Reservoir - Neerukonda Reservoir - 0.40 TMC | 2024-10-12 | 30.12.2024 | 608.26 | 72.41 | 608.26 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 117 | 3.54 | 2
20 | WIN/0085/25-26 | E14 Road | Sub-arterial Road E14 | 20-12-2024 | 07.01.2025 | 350.07 | 41.68 | 350.07 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 109 | 4.42 | 3
21 | WIN/0067/25-26 | E3 Road - Phase I | Sub-arterial Road E3 (PH-1) | 20-12-2024 | 07.01.2025 | 532.14 | 63.35 | 532.14 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 109 | 4.12 | 3
22 | WIN/0072/25-26 | E6 Road | Sub-arterial Road E6 | 2024-10-12 | 02.01.2025 | 452.96 | 53.92 | 452.96 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 4.24 | 4
23 | WIN/0073/25-26 | E8 Road | Sub-arterial Road E8 | 2024-10-12 | 07.01.2025 | 522.92 | 62.25 | 522.92 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 109 | 4.19 | 3
24 | WIN/0078/25-26 | N11 Road | Sub-arterial Road N11 | 2024-10-12 | 02.01.2025 | 419.85 | 49.98 | 419.85 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 3.48 | 3
25 | WIN/0064/25-26 | N18 Road | Sub-arterial Road N18 | 2024-10-12 | 02.01.2025 | 98.17 | 11.69 | 98.17 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 114 | 3.18 | 4
26 | WIN/0060/25-26 | N9 Road | Sub-arterial Road N9 | 2024-10-12 | 30.12.2024 | 522.39 | 62.19 | 522.39 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.24 | 3
27 | WIN/0062/25-26 | Flood Works- Gravity Canal, Krishnayapalem Reservoir | Vaagu & Reservoir - Gravity Canal - 7.83 Km; Krishnayapalem Reservoir - 0.10 TMC | 2024-10-12 | 07.01.2025 | 386.95 | 46.07 | 386.95 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 26-04-2025 | MVR Infra Projects Pvt. Ltd | 107 | 3.84 | 4
28 | WIN/0061/25-26 | Flood Works - KV, PV, Sakhamuru Reservoir | Vaagu & Reservoir - Paalavagu - 16.70 Km; Kondaveetivagu - 23.60 Km; Sakhamuru Reservoir - 0.03 TMC | 2024-10-12 | 07.01.2025 | 590.74 | 70.33 | 590.74 | Works | Open | Lumpsum | 'Jan/2025 | 'Feb/2025 | 'Mar/2025 | 2025-09-01 | 19-03-2025 | 26-04-2025 | MVR Infra Projects Pvt. Ltd | 107 | 3.98 | 3
29 | WIN/0108/25-26 | Water Distribution Centres (WDCs) | WDCs-Water Distribution Centers | 2025-09-05 | 19-06-2025 | 494.86 | 58.91 | 494.86 | Works | Open | DBO | 'Jul/2025 | 'Jul/2025 | 'Aug/2025 | 02.07.2025 | 29.08.2025 | 26.09.2025 | M/s NCC Ltd | 85 | 4.28 | 2
30 | WIN/0107/25-26 | Water Treatment Plant (WTP) | WTP (Water Treatment Plant) | 2025-09-05 | 19-06-2025 | 560.57 | 66.73 | 560.57 | Works | Open | DBO | 'Jul/2025 | 'Jul/2025 | 'Aug/2025 | 02.07.2025 | 29.08.2025 | 26.09.2025 | M/s NCC Ltd | 85 | 4.29 | 2
31 | WIN/0053/26-27 | E1 Road - Bridge with Ship Lock (From Flood pump station to N6 Road) | Bund Road - E1 / Karakatta (From Flood pump station to N6 Road) | 2026-01-05 | 2026-04-05 | 149.82 | 17.83 | 149.82 | Works | Open | Lumpsum | 'May/2026 | 'May/2026 | 'Jul/2026 | -06.05.2026 | 27.06.2026 | 25.08.2026 | M/s MVR Ltd | 114 | 4.02 | 3
32 | WIN/0053/26-27 | E1 Road - Bridge with Ship Lock (Zone - 1,2,3,5,6) (Total 90 MLD) | Bund Road - E1 / Karakatta (From N6 to N7 & N11 to N13 Road) | 2026-01-05 | 2026-04-05 | 146.47 | 17.43 | 146.47 | Works | Open | Lumpsum | 'May/2026 | 'May/2026 | 'Jul/2026 | 06.05.2026 | 27.06.2026 | to be concluded in July -26- | -M/s NCC Ltd | - | 4.72 | 3
33 | WIN/0242/25-26 | STP - Package 1 (Zone - 1,2,3,5,6) | Construction of STPs in five locations (Zone - 1,2,3,5,6) (Total 90 MLD) | 20-12-2024 | 25-08-2025 | 318.15 | 37.88 | 318.15 | Works | Open | DBO | 'Sep/2025 | 'Sep/2025 | 'Dec/2025 | 02.09.2025 | 13.11.2025 | 15.12.2025 | M/s Megha Engineering & Infrastructures Ltd. | 104 | 4.68 | 2
34 | WIN/0117/25-26 | Flood Pumping Station | Flood Pumping Station at Undavalli | 2025-12-11 | 13-11-2025 | 595.01 | 70.83 | 595.01 | Works | Open | DBO | 'Nov/2025 | 'Dec/2025 | 'Feb/2026 | 14.11.2025 | 2026-02-01 | 12.02.2026 | M/s Megha Engineering & Infrastructures Ltd. | 90 | 4.75 | 2-
35 |  | Green Buffer for Vaagus | Green Buffer for Vaagus | - | - | 184.06 | 21.91 | 184.06 | Works | Open |  | '- | '- | - | - | - | - | - | - | - | -

## APP
Appendix-2: Annual Procurement Plan (Funded by ADB/WB)
S.No. | Description of Procurement activity | Administrative Sanction | Technical year Sanction | Estimated Cost INR (Cores) | Estimated cost USD Millions | Procurement Category (Goods/ Works/ NCS/ CS) | Procurement Method (Open/ Limited/ Direct) | Item rate/ Lumpsum (EPC/DBO) | Planned issuance of NIT (month/ year) | Technical Envelope opening (Tender / RFP) | Expected date of Contract Award month/
|  | Date (dd/mm/yy) | Date (dd/mm/yy)
1 | Arterial Road E9 | 20-12-2024 | 07.01.2025 | 583.34 | 69.45 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
2 | Arterial Road N12 | 20-12-2024 | 07.01.2025 | 614.56 | 73.16 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
3 | Arterial Road N15 | 2024-10-12 | 02.01.2025 | 482.01 | 57.38 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
4 | LPS Zone - 1A | 2024-10-12 | 26-12-2024 | 448.32 | 53.37 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
5 | LPS Zone - 1B | 2024-10-12 | 26-12-2024 | 588.04 | 70 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
6 | LPS Zone - 2A | 2024-10-12 | 26-12-2024 | 542.84 | 64.62 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
7 | LPS Zone - 2B | 2024-10-12 | 26-12-2024 | 542.84 | 64.62 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
8 | LPS Zone - 3A | 20-12-2024 | 28-12-2024 | 505.53 | 60.18 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
9 | LPS Zone - 3B | 20-12-2024 | 28-12-2024 | 420.65 | 50.08 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
10 | LPS Zone - 5B | 2024-10-12 | 26-12-2024 | 603.14 | 71.8 | Works | Open | Lumpsum | 2026-12-25 | 2026-02-25 | 2026-03-25
11 | LPS Zone - 5D | 2024-10-12 | 26-12-2024 | 603.65 | 71.86 | Works | Open | Lumpsum | 2026-12-24 | 2026-02-25 | 2026-03-25
12 | LPS Zone - 6 | 2024-10-12 | 26-12-2024 | 530.83 | 63.19 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
13 | Multistorey apartment for GO TY-1 & TY-2 and Group D Employees | 2024-10-12 | 20.02.2025 | 594.54 | 70.78 | Works | Open | Lumpsum | 2026-03-25 | 2026-04-25 | 2026-05-25
14 | Multistorey apartment for MLA & AIS including External Infra works | 16-10-2024 | 01.01.2025 | 524.7 | 62.46 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
15 | Multistorey apartment for NGO Phase - 1B including External Infra works (for 9 towers) | 2024-10-12 | 20.02.2025 | 594.36 | 70.76 | Works | Open | Lumpsum | 2026-03-25 | 2026-04-25 | 2026-05-25
16 | Multistorey apartment for NGO Phase-1A including External Infra works (for 12 towers) | 2024-10-12 | 20.02.2025 | 607.5 | 72.32 | Works | Open | Lumpsum | 2026-03-25 | 2026-04-25 | 2026-05-25
17 | Multistorey Apartments for GO TY-1, GO TY-II & Group - D - Phase-II (External Infrastructure) | 2024-10-12 | 20.02.2025 | 226.26 | 26.94 | Works | Open | Lumpsum | 2026-03-25 | 2026-04-25 | 2026-05-25
18 | N6 - Utilities only | 20-12-2024 | 07.01.2025 | 232.86 | 27.72 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
19 | Reservoir - Neerukonda Reservoir - 0.40 TMC | 2024-10-12 | 30.12.2024 | 608.26 | 72.41 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
20 | Sub-arterial Road E14 | 20-12-2024 | 07.01.2025 | 350.07 | 41.68 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
21 | Sub-arterial Road E3 (PH-1) | 20-12-2024 | 07.01.2025 | 532.14 | 63.35 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
22 | Sub-arterial Road E6 | 2024-10-12 | 02.01.2025 | 452.96 | 53.92 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
23 | Sub-arterial Road E8 | 2024-10-12 | 07.01.2025 | 522.92 | 62.25 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
24 | Sub-arterial Road N11 | 2024-10-12 | 02.01.2025 | 419.85 | 49.98 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
25 | Sub-arterial Road N18 | 2024-10-12 | 02.01.2025 | 98.17 | 11.69 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
26 | Sub-arterial Road N9 | 2024-10-12 | 30.12.2024 | 522.39 | 62.19 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
27 | Vaagu & Reservoir - Gravity Canal - 7.83 Km; Krishnayapalem Reservoir - 0.10 TMC | 2024-10-12 | 07.01.2025 | 386.95 | 46.07 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
28 | Vaagu & Reservoir - Paalavagu - 16.70 Km; Kondaveetivagu - 23.60 Km; Sakhamuru Reservoir - 0.03 TMC | 2024-10-12 | 07.01.2025 | 590.74 | 70.33 | Works | Open | Lumpsum | 2026-01-25 | 2026-02-25 | 2026-03-25
29 | WDCs-Water Distribution Centers | 2025-09-05 | 19-06-2025 | 494.86 | 58.91 | Works | Open | DBO | 2026-07-25 | 2026-07-25 | 2026-08-25
30 | WTP (Water Treatment Plant) | 2025-09-05 | 19-06-2025 | 560.57 | 66.73 | Works | Open | DBO | 2026-07-25 | 2026-07-25 | 2026-08-25
31 | Bund Road - E1 / Karakatta (From Flood pump station to N6 Road) | 2026-01-05 | 2026-04-05 | 149.82 | 17.83 | Works | Open | Lumpsum | 2026-05-26 | 2026-05-26 | 2026-07-26
32 | Bund Road - E1 / Karakatta (From N6 to N7 & N11 to N13 Road) | 2026-01-05 | 2026-04-05 | 146.47 | 17.43 | Works | Open | Lumpsum | 2026-05-26 | 2026-05-26 | 2026-07-26
33 | Construction of STPs in five locations (Zone - 1,2,3,5,6) (Total 90 MLD) | 20-12-2024 | 25-08-2025 | 318.15 | 37.88 | Works | Open | DBO | 2026-09-25 | 2026-09-25 | 2026-12-25
34 | Flood Pumping Station at Undavalli | 2025-12-11 | 13-11-2025 | 595.01 | 70.83 | Works | Open | DBO | 2026-11-25 | 2026-12-25 | 2026-02-25
35 | Green Buffer for Vaagus | - | - | 184.06 | 21.91 | Works | Open

## KPI
Appendix-3: Status of Procurement & Compliance KPIs
S. No | Project Name | Estimated Cost (₹ cr.) | Tender Publish Date | LOA Issue | Agreement Date | Contractor | KPI-2: Procurement cycle time (NIT to Agreement signing date) (Days) | KPI-3 Financial quote (+/-) | KPI-3 Avg no. of bidders
1 | LPS Zone - 2A | ₹ 542.84 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.19 | 3
2 | LPS Zone - 2B | ₹ 542.84 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.19 | 3
3 | LPS Zone – 6 | ₹ 530.83 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 116 | 3.64 | 3
4 | N6 - Utilities only | ₹ 232.86 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 109 | 4.02 | 3
5 | N11 Road with Utilities | ₹ 419.85 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 3.48 | 3
6 | N18 Road with Utilities | ₹ 98.17 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 114 | 3.18 | 4
7 | Road N9 Road with Utilities | ₹ 522.39 | 2025-02-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 116 | 4.24 | 3
8 | N12 Road with Utilities | ₹ 614.56 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 109 | 3.94 | 3
9 | N15 Road with Utilities | ₹ 482.01 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 114 | 3.32 | 3
10 | E14 Road with Utilities | ₹ 350.07 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 109 | 4.42 | 3
11 | E9 Road with Utilities | ₹ 583.34 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 109 | 3.84 | 3
12 | E3 (PH-1) Road with Utilities | ₹ 532.14 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 109 | 4.12 | 3
13 | E6 Road with Utilities | ₹ 452.96 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 4.24 | 4
14 | E8 | ₹ 522.92 | 2025-09-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 109 | 4.19 | 3
15 | Multistorey apartment for GO TY-1 & TY-2 and Group D Employees 14 Towers | ₹ 594.54 | 24-03-2025 | 14-05-2025 | 2025-04-08 | M/s. Shapoorji & Pallonji Co Ltd​ | 134 | 4.39 | 3
16 | LPS Zone - 3A | ₹ 505.53 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 114 | 4.24 | 3
17 | LPS Zone - 3B | ₹ 420.65 | 2025-04-01 | 19-03-2025 | 28-04-2025 | M/s Megha Engineering & Infrastructures Ltd. | 114 | 3.96 | 3
18 | LPS Zone - 5B | ₹ 603.14 | 31-12-2024 | 19-03-2025 | 28-04-2025 | M/s R V R Projects Private Limited | 118 | 3.77 | 3
19 | LPS Zone - 5D | ₹ 603.65 | 31-12-2024 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 118 | 4.12 | 3
20 | Multistorey apartment for NGO Phase - 1B including External Infra works (for 9 towers) | ₹ 594.36 | 24-03-2025 | 14-05-2\ | 14-07-2025 | M/s Larsen & Toubro Limited | 112 | 4.4 | 3
25
21 | Multistorey apartment for NGO Phase-1A including External Infra works (for 12 towers) | ₹ 607.50 | 24-03-2025 | 14-05-2025 | 14-07-2025 | M/s Larsen & Toubro Limited | 112 | 4.41 | 3
22 | Reservoir - Neerukonda Reservoir - 0.40 TMC | ₹ 608.26 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 117 | 3.54 | 2
23 | Vaagu & Reservoir - Gravity Canal - 7.83 Km; Krishnayapalem Reservoir - 0.10 TMC | ₹ 386.95 | 2025-09-01 | 19-03-2025 | 26-04-2025 | MVR Infra Projects Pvt. Ltd | 107 | 3.84 | 4
24 | Vaagu & Reservoir - Palavagu - 16.70 Km; Kondaveetivagu - 23.60 Km; Sakhamuru Reservoir - 0.03 TMC | ₹ 590.74 | 2025-09-01 | 19-03-2025 | 26-04-2025 | MVR Infra Projects Pvt. Ltd | 107 | 3.98 | 3
25 | Multistorey apartment for MLA & AIS including External Infra works | ₹ 524.70 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s. NCC LIMITED | 117 | 4.1 | 3
26 | Multistorey Apartments for GO TY-1, GO TY-II & Group - D - Phase-II (External Infrastructure) | ₹ 226.26 | 24-03-2025 | 14-05-2025 | 14-07-2025 | M/s. Shapoorji & Pallonji Co Ltd​ | 112 | 4.39 | 3
27 | LPS Zone - 1A | ₹ 448.32 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 117 | 3.96 | 3
28 | LPS Zone - 1B | ₹ 588.04 | 2025-01-01 | 19-03-2025 | 28-04-2025 | M/s BSR Infratech India Limited | 117 | 4.04 | 3
29 | WDCs-Water Distribution Centers | ₹ 494.86 | 02.07.2025 | 29.08.2025 | 26.09.2025 | M/s NCC Ltd | 85 | 4.28 | 2
30 | WTP (Water Treatment Plant) | ₹ 560.57 | 02.07.2025 | 29.08.2025 | 26.09.2025 | M/s NCC Ltd | 85 | 4.29 | 2
31 | Bund Road - E1 / Karakatta (From Flood pump station to N6 Road) | ₹ 149.82 | -06.05.2026 | 27.06.2026 | 25.08.2026 | M/s MVR Ltd | 114 | 4.02 | 3
32 | Bund Road - E1 / Karakatta (From N6 to N7 & N11 to N13 Road) | ₹146.47 | 06.05.2026 | 27.06.2026 | to be concluded in July -26- | -M/s NCC Ltd | - | 4.72 | 3
33 | Construction of STPs in five locations (Zone - 1,2,3,5,6) (Total 90 MLD) | ₹ 318.15 | 02.09.2025 | 13.11.2025 | 15.12.2025 | M/s Megha Engineering & Infrastructures Ltd. | 104 | 4.68 | 2
34 | Flood Pumping Station at Undavalli | 595.01 | 14.11.2025 | 2026-02-01 | 12.02.2026 | M/s Megha Engineering & Infrastructures Ltd. | 90 | 4.75 | 2-
35 | Green Buffer for Vaagus | ₹ 184.06 | - | - | - | - | - | - | -