## Construction Progress
Project Number | Project Name | HOD | Funding Agency | Contractor | PMC | Division | Assistant Engineer / Assistant Executive Engineer | Deputy Executive Engineer | Executive Engineer | Superintending Engineer | Chief Engineer | Start Date | End Date- Fastrack | End Date- Contractual | Project BOQ Value in Rs Crores | Tender Premium (%) | Cost | Physical Target - Fastrack | Work Completed | Work Completed Cost | Variance (%) | Status | Work Cleared | Work Cleared Cost | Work Certified (%) | Work Certified Amt | Bills Paid (%) | Bills Paid Amt | Land Acquisition Area | Total Area
WIN/0010/24-25 | Zone - 1A | ADCL | WB+ADB | BSR | Nippon Koei | LPS Infra | Gouse Basha | Pamarthi Radha Krishna | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 334.96 | 3.96 | 3501916868.42 | 51.89% | 32.26% | 1080529715.9 | -19.63% | Delay | 33.67% | 1127667472.38 | 23.97% | 839500000 | 20.93% | 733100000 | 2.05 | 107.98
WIN/0011/24-25 | Zone - 1B | ADCL | WB+ADB | BSR | Nippon Koei | LPS Infra | Gouse Basha | Pamarthi Radha Krishna | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 447.15 | 4.04 | 4683722299.22 | 53.25% | 24.36% | 1089407200.32 | -28.89% | Delay | 24.54% | 1097165503.4 | 18.35% | 859300000 | 15.77% | 738600000 | 1.76 | 162.9
WIN/0014/24-25 | Zone - 2A | ADCL | WB+ADB | BSR | Aarvee | LPS Infra | Undavalli Gopi | Pulaguru Hanumantha Reddy | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 399.85 | 4.19 | 4186282140.50 | 57.63% | 30.38% | 1214709649.95 | -27.25% | Delay | 31.76% | 1269946990.66 | 24.25% | 1015300000 | 20.89% | 874700000 | 1.96 | 169
WIN/0016/24-25 | Zone - 2B | ADCL | WB+ADB | BSR | Aarvee | LPS Infra | Undavalli Gopi | Pulaguru Hanumantha Reddy | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 413.84 | 4.19 | 4323748565.56 | 53.99% | 28.07% | 1161736565.09 | -25.91% | Delay | 28.2% | 1167111856.09 | 21.52% | 930400000 | 18.68% | 807600000 | 0 | 163.74
WIN/0022/24-25 | Zone - 5A | ADCL | NABARD | BSR | Tractebel | LPS Infra | G.V. Siva Ganesh | SRIKANTH SADINENI | Chalamalasetti Naga Venkat | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 745.69 | 4.09 | 7805738401.23 | 42.82% | 24.94% | 1871858838.45 | -17.88% | Delay | 25.64% | 1924922570.52 | 18.08% | 1411300000 | 12.58% | 982300000 | 1.72 | 264.44
WIN/0024/24-25 | Zone - 5C | ADCL | NABARD | BSR | Tractebel | LPS Infra | CHETTIPOGU RAVI KUMAR | Nallapu Srikanth | Chalamalasetti Naga Venkat | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 580.15 | 4.02 | 6058797099.19 | 55.12% | 34.47% | 1999481762.06 | -20.66% | Delay | 34.65% | 2009936691.98 | 28.72% | 1740100000 | 24.37% | 1476400000 | 0.53 | 213.43
WIN/0025/24-25 | Zone - 5D | ADCL | WB+ADB | BSR | Tractebel | LPS Infra | T. Nagendra Babu | Chalamalasetti Naga Venkat | Chalamalasetti Naga Venkat | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 448.58 | 4.12 | 4704150741.19 | 60.79% | 25.41% | 1139710317.96 | -35.38% | Delay | 25.95% | 1164160990.3 | 18.67% | 878100000 | 15.74% | 740400000 | 3.96 | 158.85
WIN/0009/24-25 | Zone - 3B | ADCL | WB+ADB | MEIL | Tractebel | LPS Infra | Nagarjuna Y | Jagan Mohan Reddy A | Dr.Neelam Sivalinga Rao | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 300.69 | 3.96 | 3136831032.4 | 45.18% | 18.51% | 556564357.16 | -26.67% | Delay | 18.64% | 560410804.08 | 14.63% | 458900000 | 11.09% | 347900000 | 0.3 | 119.29
WIN/0021/24-25 | Zone - 6 | ADCL | WB+ADB | MEIL | Aarvee | LPS Infra | Korukonda Sri Harsha | Jagan Mohan Reddy A | Dr.Neelam Sivalinga Rao | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 377.91 | 3.64 | 3940101283.74 | 54.8% | 12.29% | 464519175.11 | -42.51% | Delay | 12.37% | 467604587.21 | 8.36% | 329500000 | 9.11% | 359000000 | 5.03 | 146.29
WIN/0013/24-25 | Zone - 9 | ADCL | NaBFID | MEIL | Tractebel | LPS Infra | Katakam Hareesh Kumar | SRIKANTH SADINENI | Chalamalasetti Naga Venkat | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 1994.05 | 4.10 | 20777046217.52 | 50.46% | 12.19% | 2429757528.18 | -38.28% | Delay | 12.75% | 2543300687.35 | 9.72% | 2020200000 | 9.68% | 2011900000 | 20.23 | 741.76
WIN/0007/24-25 | Zone - 9A | ADCL | Other Funds | MEIL | Tractebel | LPS Infra | Matcha Sai Chand | Pandala Seshagiri Rao | Manepalli B D N V Prasad | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 1233.78 | 4.15 | 12871892924.10 | 63.83% | 16.3% | 2010736849.32 | -47.53% | Delay | 16.33% | 2014380855.73 | 11.10% | 1428600000 | 10.83% | 1394100000 | 13.11 | 469.57
WIN/0020/24-25 | Zone - 12A | ADCL | NABARD | MEIL | Nippon Koei | LPS Infra | Namburu Rajasekhar | M Mukesh Kumar | Perikala Venkateswarlu | Duddu Vijaya Kumari | R Gopala Krishna Reddy | 28-04-2025 | 27-10-2027 | 27-04-2028 | 1483.16 | 4.20 | 15356080373.76 | 49.57% | 12.12% | 1797219057.85 | -37.45% | Delay | 12.77% | 1894722338.84 | 10.55% | 1620000000 | 10.99% | 1688100000 | 55.32 | 540.02
WIN/0008/24-25 | Zone - 3A | ADCL | WB+ADB | RVR | Tractebel | LPS Infra | S Manikanta | Pulaguru Hanumantha Reddy | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 377.2 | 4.24 | 3933191352.81 | 48% | 25.43% | 959123965.02 | -22.58% | Delay | 25.44% | 959766139.25 | 20.90% | 821900000 | 16.57% | 651600000 | 0.56 | 130.01
WIN/0018/24-25 | Zone - 4 | ADCL | NaBFID | RVR | Aarvee | LPS Infra | G N S Bhushan | P.V Nagendra Kumar | Manepalli B D N V Prasad | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 803.98 | 4.24 | 8441087996.37 | 48.44% | 18.63% | 1501943616.39 | -29.81% | Delay | 18.66% | 1503997513.91 | 14.03% | 1184600000 | 10.97% | 926300000 | 4.2 | 259.78
WIN/0023/24-25 | Zone - 5B | ADCL | WB+ADB | RVR | Tractebel | LPS Infra | Undavalli Gopi | Pulaguru Hanumantha Reddy | M Ravi Kumar | Koripella Srinivasa Rao | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 463.28 | 3.77 | 4833670686.21 | 48.7% | 21.51% | 996337559.01 | -27.19% | Delay | 21.52% | 996760265.47 | 15.87% | 767200000 | 11.11% | 537000000 | 0.41 | 228.22
WIN/0026/24-25 | Zone - 10 | ADCL | HUDCO | RVR | Aarvee | LPS Infra | Korukonda Sri Harsha | V V Nagendra Kumar Pyna | Manepalli B D N V Prasad | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 1051.08 | 4.12 | 10928969317.27 | 49.26% | 14.5% | 1523749809.66 | -34.77% | Delay | 14.67% | 1541973603.07 | 10.31% | 1126400000 | 8.93% | 975500000 | 11.1 | 471.87
WIN/0012/24-25 | Zone - 7 | ADCL | NABARD | L&T | Nippon Koei | LPS Infra | CHETTIPOGU RAVI KUMAR | Nallapu Srikanth | Chalamalasetti Naga Venkat | Koripella Srinivasa Rao | Ch Dhanunjaya | 24-04-2025 | 23-10-2027 | 23-04-2028 | 794.63 | 3.94 | 8098897533.46 | 48.64% | 26.03% | 2068691018.57 | -22.6% | Delay | 29.66% | 2356705295.68 | 22.16% | 1794600000 | 20.45% | 1656500000 | 4.64 | 340.37
WIN/0019/24-25 | Zone - 12 | ADCL | NaBFID | NCC | Nippon Koei | LPS Infra | Kommineni Purandhara Chakravarthy | Gudla L D V Santhosh | Dr.Neelam Sivalinga Rao | Renati Hanumantha Reddy | Ch Dhanunjaya | 28-04-2025 | 27-10-2027 | 27-04-2028 | 2040.68 | 4.32 | 21296041953.96 | 45.34% | 11.13% | 2270450828.48 | -34.21% | Delay | 11.42% | 2331200516.23 | 8.39% | 1786000000 | 7.65% | 1628400000 | 42.67 | 737.18
WIN/0273/25-26 | Zone - 8 | ADCL | Other Funds | MEIL | LASA | LPS Infra | Shaik Karimulla | Nadella Hari Prasad | Perikala Venkateswarlu | Duddu Vijaya Kumari | R Gopala Krishna Reddy | 06-02-2026 | 05-08-2028 | 05-02-2029 | 1301.4 | 4.03 | 13580019392.34 | 9.1% | 4.52% | 587654588.77 | -4.58% | Delay | 4.79% | 623815115.67 | 3.28% | 446100000 | 3.52% | 478100000 | 10.81 | 157.64
WIN/0031/26-27 | AQCC | AGICL | Other Funds | L&T | Nippon Koei | H&B Offices | V Gopi Naik |  | Paidi Vinodh Kumar |  | Punnam V K Bhaskar | 10-03-2026 | 30-11-2026 | 30-11-2026 | 103.96 | 4.36 | 1039600000 | 100% | 34.69% | 360601893.6 | -65.31% | Delay | 37.63% | 391166133.6 | 28.85% | 299900000 | 11.96% | 124300000 | 0 | 49.69
WIN/0038/26-27 | Governor's Residence Complex | AGICL | Other Funds | BSR | Nippon Koei | H&B Buildings | Sai Kiran Namani | Gurugubelli Appala Naidu | MV Vidya Sagar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 02-05-2026 | 01-05-2027 | 01-05-2027 | 162.44 | 4.63 | 1699200000 | 31.07% | 6.89% | 110776825.47 | -24.18% | Delay | 7.64% | 122870738.69 | 0.36% | 6200000 | 0.00% | 0 | 0.7 | 11.68
WIN/0242/25-26 | STP - Package 1 (Zone - 1,2,3,5,6) | ADCL | WB+ADB | MEIL | Aarvee | LPS Infra | PR Ashok Babu | Kuna Seshagiri Rao | Srinivas Rao B | Duddu Vijaya Kumari | R Gopala Krishna Reddy | 15-12-2025 | 14-06-2028 | 14-06-2028 | 262.48 | 4.68 | 2747630470.48 | 11.13% | 0% | 0 | -11.13% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0 | 65.53
WIN/0243/25-26 | STP - Package 2 (Zone - 4,7,9A,10) | ADCL | Other Funds | MEIL | Aarvee | LPS Infra | PR Ashok Babu | Kuna Seshagiri Rao | Srinivas Rao B | Duddu Vijaya Kumari | R Gopala Krishna Reddy | 15-12-2025 | 14-06-2028 | 14-06-2028 | 290.93 | 4.70 | 3046030707.36 | 10.79% | 0% | 0 | -10.79% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0.34 | 45.16
WIN/0244/25-26 | STP - Package 3 (Zone - 12,12A) | ADCL | Other Funds | MEIL | Aarvee | LPS Infra | PR Ashok Babu | Kuna Seshagiri Rao | Srinivas Rao B | Duddu Vijaya Kumari | R Gopala Krishna Reddy | 15-12-2025 | 14-06-2028 | 14-06-2028 | 207.86 | 4.65 | 2175253567.81 | 11.17% | 0% | 0 | -11.17% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0 | 84.08
WIN/0286/25-26 | PEB Structure (4th Shed) | AGICL | Other Funds | NCC | NA | H&B Offices | Guttameda Vinod Kumar | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 20-02-2026 | 19-08-2026 | 19-08-2026 | 51.73 | 4.23 | 517319595.45 | 100% | 80.9% | 418511552.72 | -19.1% | Delay | 80.9% | 418511552.72 | 72.81% | 376600000 | 73.55% | 380500000 | 0 | 0.92
WIN/0283/25-26 | Project Office Balance Works | AGICL | Other Funds | KPC | NA | H&B Offices | Noonsavathu Krishna Kumar Naik | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 20-02-26 | 30-09-2026 | 19-08-2026 | 76.14 | 4.75 | 761400000 | 100% | 90% | 685260000 | -10% | Delay | 90% | 685260000 | 82.83% | 630700000 | 92.76% | 706400000 | 0 | 4.41
WIN/0182/25-26 | E3 Road - Phase III | ADCL | Other Funds | NCC | LASA | Trunk Infra | Juluri Naga Raja Kumar | Appaji Yandrapu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 09-01-2026 | 31-08-2026 | 08-07-2026 | 61.67 | 4.05 | 641700000 | 100% | 57.12% | 352265384.98 | -42.88% | Delay | 57.55% | 354902160.69 | 25.32% | 162500000 | 25.54% | 163900000 | 0 | 45.45
WIN/0133/25-26 | E3 Phase III - Extn. upto NH-16 | ADCL | NA | NCC | LASA | Trunk Infra | Kathi Nagarjuna | Appaji Yandrapu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 27-02-2026 | 27-12-2026 | 26-02-2028 | 511.84 | 4.05 | 5325700000 | 0% | 10.21% | 522581869.87 | 10.21% | On_track | 10.35% | 529765269.95 | 8.46% | 450300000 | 9.74% | 518700000 | 0 | 0
WIN/0117/25-26 | Flood Pumping Station - 2(8400 Cusec) | ADCL | WB+ADB | MEIL | TYPSA | Flood Mitigation | Vempalli Mohammad Rafi | Eraga Sreenivasulu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 12-02-26 | 11-02-28 | 11-02-28 | 423.64 | 4.75 | 4437600000 | 0% | 0% | 0 | 0% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 7.35 | 18.23
WIN/0053/26-27 | E1 Road - Bridge with Ship Lock | ADCL | HUDCO | MEIL | TYPSA | Trunk Infra |  |  |  |  | Tumeti Moses Kumar | 14-05-2026 | 14-05-27 | 14-05-27 |  | 4.80 | 585314024.95 | 0% | 0% | 0 | 0% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 5.15 | 36.81
WIN/0072/25-26 | E6 Road | ADCL | WB+ADB | RVR | Aarvee | Trunk Infra | Ravi Teja Murala | Bandaru Katama Raju | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 320.36 | 4.24 | 3372857921.00 | 66.77% | 38.59% | 1236216052.02 | -28.18% | Delay | 38.59% | 1236180890.24 | 30.91% | 1042600000 | 28.15% | 949400000 | 0.15 | 135.98
WIN/0094/25-26 | E2 Road | ADCL | HUDCO | BSR | Aarvee | Trunk Infra | Mareedu Eswer sai | Venkata Rattaiah Kunche | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 151.27 | 4.10 | 1574741197.54 | 88.44% | 25.72% | 389120630.11 | -62.72% | Delay | 25.75% | 389580785.96 | 22.45% | 353500000 | 21.00% | 330700000 | 0.17 | 62.37
WIN/0061/25-26 | Flood Works - KV, PV, Sakhamuru Reservoir | ADCL | WB+ADB | MVR | TYPSA | Flood Mitigation | Ogirala Chaitanya | Yalla Srinivas | Kalluri Basaveswara Rao | Kontham Rama Mohana Rao | Narasimha Murthy B | 26-04-2025 | 25-12-2026 | 25-04-2027 | 462.26 | 3.98 | 4806533674.76 | 79.51% | 54.02% | 2497229482.74 | -25.49% | Delay | 57.48% | 2657104466.08 | 52.50% | 2523400000 | 45.67% | 2195000000 | 30.85 | 651.67
WIN/0062/25-26 | Flood Works- Gravity Canal, Krishnayapalem Reservoir | ADCL | WB+ADB | MVR | TYPSA | Flood Mitigation | Ogirala Chaitanya | Yalla Srinivas | Kalluri Basaveswara Rao | Kontham Rama Mohana Rao | Narasimha Murthy B | 26-04-2025 | 25-12-2026 | 25-04-2027 | 303.73 | 3.84 | 3153958166.45 | 87.71% | 70.26% | 2133949846.43 | -17.45% | Delay | 75.35% | 2288757099.71 | 72.79% | 2295700000 | 67.39% | 2125300000 | 8.59 | 305.05
WIN/0077/25-26 | Flood Works - Neerukonda Reservoir | ADCL | WB+ADB | NCC | TYPSA | Flood Mitigation | Dasari Manoj varma | Sajja Ratnakumar | Kalluri Basaveswara Rao | Kontham Rama Mohana Rao | Narasimha Murthy B | 06-05-2025 | 05-01-2027 | 05-05-2027 | 470.75 | 3.54 | 4874132706.10 | 69.43% | 55.02% | 2589896130.29 | -14.41% | Delay | 55.52% | 2613654517.66 | 50.13% | 2443400000 | 54.30% | 2646800000 | 0 | 441.13
WIN/0031/24-25 | Happy Nest | AGICL | HUDCO | NCC | Feedback | H&B Buildings | Ponnana Sai Aravindh, Galipothu Pavan Kumar | K Rohith Kumar | M. Yajurved Reddy | M. Chandra Mohan Rao | K Nagaraju | 23-04-2025 | 22-12-2026 | 22-04-2027 | 840.69 | 4.68 | 8563166421.89 | 73.76% | 20.69% | 1739380496.23 | -53.07% | Delay | 20.7% | 1739997708.97 | 19.32% | 1654400000 | 18.74% | 1604600000 | 0 | 14.49
WIN/0097/25-26 | E12 Road | ADCL | Other Funds | BSR | MaRS | Trunk Infra | Kondeti Venkata Rama Saran Teja | Rohit Kumar Muppavarapu | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 245.45 | 4.14 | 2556079583.13 | 89.99% | 31.26% | 767256179.6 | -58.73% | Delay | 31.31% | 768374222.4 | 25.70% | 657000000 | 23.54% | 601700000 | 2.34 | 96.44
WIN/0064/25-26 | N18 Road | ADCL | WB+ADB | BSR | Aarvee | Trunk Infra | Bojjanapalli Naga Srikanth | MADHU THUMMALAPALLI | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 65.62 | 3.18 | 676955495.51 | 100% | 63.89% | 419246600.84 | -36.11% | Delay | 64.03% | 420169200.96 | 60.39% | 408800000 | 60.14% | 407100000 | 0 | 25.3
WIN/0138/25-26 | Tower 3 and 4 - Structure | AGICL | Other Funds | L&T | Colliers | H&B Offices | Ramakrishna | Niteesh Komatineni | Paidi Vinodh Kumar | P Ankamma Choudary | Sudhakar Reddy Gopidi | 04-08-2025 | 03-08-2027 | 03-08-2027 | 1236.94 | 4.54 | 13038537689.57 | 55.87% | 21.58% | 2668978482.32 | -34.29% | Delay | 21.75% | 2690885652.75 | 26.76% | 3489300000 | 13.33% | 1737900000 | 0 | 1.08
WIN/0041/24-25 | Tower 1 and 2 - Structure | AGICL | HUDCO | SPCL | Colliers | H&B Offices | Nallagondla Pavan Kumar | Chilukuri Lakshmi Narayana | MV Vidya Sagar | P Ankamma Choudary | Mukkamala Venkateswara Rao | 04-08-2025 | 03-08-2027 | 03-08-2027 | 1424.88 | 4.50 | 14871135294.51 | 61.8% | 25.15% | 3584250795.46 | -36.65% | Delay | 25.23% | 3594677942.26 | 23.62% | 3513000000 | 19.07% | 2835900000 | 0 | 1.08
WIN/0039/24-25 | GAD Tower - Structure | AGICL | Other Funds | NCC | Colliers | H&B Offices | Thiramdasu Gowtham Kumar / Mullapudi Srikanth | SHG Phani Kumar | A S S S Venkateswara Rao | P Ankamma Choudary | Mukkamala Venkateswara Rao | 04-08-2025 | 03-08-2027 | 03-08-2027 | 847.09 | 4.53 | 8824725285.43 | 51.42% | 24.11% | 2037039552.15 | -27.31% | Delay | 24.14% | 2040222208.12 | 21.41% | 1889500000 | 19.09% | 1684900000 | 0 | 0.54
WIN/0147/25-26 | GOs and Group D employees - Housing | AGICL | WB+ADB | SPCL | Feedback | H&B Buildings | Noonsavathu Krishna Kumar Naik | Marreddy Hemambaradhara Reddy | Paidi Vinodh Kumar | Maram Rama Mohan | Bitra Srinivasa Rao | 14-07-2025 | 30-09-2026 | 13-01-2027 | 492.77 | 4.60 | 5144055295.97 | 99.7% | 25.99% | 1280553750.57 | -73.71% | Delay | 29.67% | 1461929546.16 | 24.63% | 1266900000 | 21.07% | 1083700000 | 0.26 | 18.14
WIN/0034/24-25 | GOs and Group D employees - External Infra | AGICL | WB+ADB | SPCL | Bureau Veritas | H&B Buildings | Guttameda Vinod Kumar | Nallapu Srikanth | Paidi Vinodh Kumar | Maram Rama Mohan | Bitra Srinivasa Rao | 04-08-2025 | 30-09-2026 | 03-02-2027 | 189.49 | 4.39 | 1947283492.95 | 100% | 4.28% | 81099387.59 | -95.72% | Delay | 5.29% | 100196146.05 | 5.41% | 105300000 | 0.00% | 0 | 0.26 | 18.14
WIN/0146/25-26 | NGO (Housing+Ext. Infra) - 9 Towers | AGICL | WB+ADB | L&T | Tractebel | H&B Buildings | Kalla Anuraju | Vadlamudi Manmadhaiah | M. Yajurved Reddy | K. Kedareswara Rao | Bitra Srinivasa Rao | 14-07-2025 | 31-10-2026 | 13-01-2027 |  | 4.41 | 5060688047.24 | 100% | 30.21% | 1563851563.24 | -69.79% | Delay | 33.61% | 1739652946.11 | 23.02% | 1164800000 | 10.46% | 529500000 | 0 | 25.69
WIN/0145/25-26 | NGO (Housing+Ext. Infra) - 12 Towers | AGICL | WB+ADB | L&T | Tractebel | H&B Buildings | Javisetty Venkaiah | Vadlamudi Manmadhaiah | M. Yajurved Reddy | K. Kedareswara Rao | Bitra Srinivasa Rao | 14-07-2025 | 13-01-2027 | 13-01-2027 |  | 4.40 | 5171042870.71 | 100% | 22.16% | 1172305897.5 | -77.84% | Delay | 22.9% | 1211215689.18 | 19.48% | 1007400000 | 15.11% | 781100000 | 0 | 23.64
WIN/0102/25-26 | N16 Road | ADCL | NABARD | BSCPL | MaRS | Trunk Infra | PITCHUKA AJAYKUMAR | Ashok Yanikapati | Manchikalapati Vaasu Charan | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 184.13 | 4.26 | 1919218329.69 | 70.12% | 38.15% | 702452672.31 | -31.97% | Delay | 38.55% | 709911592.12 | 35.33% | 678100000 | 34.59% | 663900000 | 0 | 103.52
WIN/0082/25-26 | E11 Road | ADCL | HUDCO | MEIL | LASA | Trunk Infra | Dasari Manoj varma | Sajja Ratnakumar | Kalluri Basaveswara Rao | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 150.38 | 4.35 | 1569229619.44 | 82.7% | 28.42% | 427386835.96 | -54.28% | Delay | 28.56% | 429456690.37 | 26.36% | 413700000 | 25.27% | 396600000 | 0.68 | 85.03
WIN/0101/25-26 | N14 Road | ADCL | Other Funds | RVR | MaRS | Trunk Infra | Jonna Siva Kishore | Venkata Rattaiah Kunche | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 242.9 | 4.05 | 2527391126.59 | 61% | 35.8% | 869690415.64 | -25.19% | Delay | 35.87% | 871214976.46 | 29.58% | 747600000 | 26.56% | 671200000 | 0.4 | 93.79
WIN/0100/25-26 | N10 Road | ADCL | NABARD | RVR | MaRS | Trunk Infra | Bhanu Shashank Gudapati | Kurakula Veera Prakasa Rao | Manchikalapathi Vaasu Charan | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 582.98 | 3.90 | 6057154831.87 | 62.6% | 22.44% | 1308039253.05 | -40.16% | Delay | 22.77% | 1327164277.1 | 18.06% | 1093800000 | 13.50% | 818000000 | 5.61 | 191.33
WIN/0099/25-26 | N8 Road | ADCL | HUDCO | NCC | LASA | Trunk Infra | Saisaran Boyina | Venkata Rattaiah Kunche | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 581.55 | 4.04 | 6050451103.56 | 90.05% | 13.88% | 806932405.08 | -76.17% | Delay | 14.01% | 814816795.25 | 11.76% | 711200000 | 10.92% | 660900000 | 17.34 | 155.18
WIN/0103/25-26 | N17 Road | ADCL | Other Funds | BSCPL | MaRS | Trunk Infra | vamsi krishna Nadella | Veera Babu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 179.46 | 4.06 | 1867452392.14 | 81.1% | 32.7% | 586742420.03 | -48.41% | Delay | 32.77% | 588163539.51 | 25.64% | 478800000 | 21.26% | 397100000 | 0.72 | 81.76
WIN/0079/25-26 | E5 Road | ADCL | HUDCO | BSR | Aarvee | Trunk Infra | Merla Veeraiah Chowdary | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 539.57 | 4.32 | 5628829258.12 | 91.9% | 33.57% | 1811588725.7 | -58.32% | Delay | 33.62% | 1814306934.07 | 30.38% | 1710200000 | 27.45% | 1545400000 | 18.86 | 502.94
WIN/0083/25-26 | E13 Road | ADCL | HUDCO | RVR | LASA | Trunk Infra | Kondeti Venkata Rama Saran Teja | Rohit Kumar Muppavarapu | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 199.29 | 4.30 | 2078565361.75 | 59.18% | 25.5% | 508176797.29 | -33.68% | Delay | 25.56% | 509438609.89 | 24.82% | 515900000 | 18.57% | 385900000 | 3.35 | 156.93
WIN/0091/25-26 | N4 Road | ADCL | Other Funds | BSCPL | MaRS | Trunk Infra | Mahesh Suraboina | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 26-04-2025 | 25-12-2026 | 25-04-2027 | 236.44 | 4.22 | 2464163069.37 | 75.95% | 32.1% | 758871028.97 | -43.86% | Delay | 32.09% | 758797245.98 | 29.60% | 729300000 | 24.99% | 615800000 | 2.88 | 79.93
WIN/0088/25-26 | N1 Road | ADCL | Other Funds | BSR | Voyants | Trunk Infra | Merla Veeraiah Chowdary | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 120.25 | 4.02 | 1250833400.65 | 91.05% | 0% | 0 | -91.05% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 19.76 | 43.4
WIN/0096/25-26 | E10 Road | ADCL | Other Funds | MEIL | MaRS | Trunk Infra | Saisaran Boyina | Venkata Rattaiah Kunche | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 283.65 | 4.30 | 2958417351.96 | 63.44% | 16.67% | 472968934.18 | -46.77% | Delay | 17.27% | 489844082.05 | 14.57% | 431100000 | 13.56% | 401100000 | 1.06 | 108.64
WIN/0089/25-26 | N2 Road | ADCL | Other Funds | BSR | Voyants | Trunk Infra | Merla Veeraiah Chowdary | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 107.59 | 3.95 | 1118412142.45 | 79.6% | 0.66% | 7147635.07 | -78.93% | Delay | 0.68% | 7313510.23 | 0.56% | 6300000 | 0.67% | 7500000 | 8.51 | 25.65
WIN/0098/25-26 | N7 Road | ADCL | Other Funds | RVR | MaRS | Trunk Infra | Gandreddi Jagdish Kumar | Dr. P Ganapati Naidu | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 436.05 | 4.10 | 4539247883.27 | 60.98% | 21.68% | 945430706.97 | -39.3% | Delay | 21.68% | 945541469.18 | 17.58% | 797900000 | 15.31% | 695000000 | 5.09 | 146.1
WIN/0080/25-26 | E7 Road | ADCL | HUDCO | BSR | Aarvee | Trunk Infra | ASHOK PINNAMANENI | Miskin Shaik | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 354.84 | 4.10 | 3693874927.41 | 91.69% | 24.72% | 877135808.6 | -66.98% | Delay | 24.83% | 881164259.01 | 21.35% | 788500000 | 20.53% | 758500000 | 2.01 | 170.47
WIN/0090/25-26 | N3A and N3B Road | ADCL | Other Funds | BSCPL | Voyants | Trunk Infra | Mahesh Suraboina | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 148.76 | 4.03 | 1547540481.22 | 77.83% | 25.58% | 380468625.1 | -52.25% | Delay | 25.59% | 380605452.31 | 23.23% | 359400000 | 17.98% | 278200000 | 1.35 | 56.74
WIN/0095/25-26 | E4 Road | ADCL | HUDCO | MEIL | Aarvee | Trunk Infra | K Naveen Kumar | Bandaru Katama Raju | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 496.18 | 3.90 | 5155308550.03 | 70.98% | 13.19% | 654263749.35 | -57.79% | Delay | 13.34% | 662044907.24 | 10.99% | 566500000 | 9.92% | 511300000 | 8.27 | 218.3
WIN/0092/25-26 | N5 Road | ADCL | Other Funds | NCC | Voyants | Trunk Infra | Varaprasadu Golimi | Bandaru Katama Raju | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 67.84 | 4.13 | 706371502.45 | 93.6% | 28.13% | 190821979.14 | -65.47% | Delay | 28.8% | 195349670.73 | 21.74% | 153600000 | 17.35% | 122600000 | 0.72 | 23.65
WIN/0093/25-26 | N13 Road | ADCL | HUDCO | RVR | LASA | Trunk Infra | Subrahmanyam Mallavalli | Kanhaiya Charan | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 244.5 | 3.93 | 2541054800.51 | 61.68% | 35.99% | 880050002.15 | -25.68% | Delay | 36.16% | 884162927.04 | 33.30% | 846200000 | 26.89% | 683400000 | 1.61 | 156.95
WIN/0104/25-26 | E3 Road - Phase II | ADCL | Other Funds | NCC | MaRS | Trunk Infra | Vukoti Sivagangadhar Rao | Appaji Yandrapu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 28-04-2025 | 27-12-2026 | 27-04-2027 | 180.95 | 4.15 | 1884551396.80 | 94.36% | 41.12% | 744027803.96 | -53.24% | Delay | 42.61% | 770992965.71 | 36.76% | 692800000 | 36.38% | 685600000 | 3.73 | 73.25
WIN/0087/25-26 | E16 Road | ADCL | NABARD | NCC | Voyants | Trunk Infra | Gudiseva Sai Krishna | AKKIRAJU CHANDRASEKHAR | Manchikalapati Vaasu Charan | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 145.35 | 4.20 | 1514545141.51 | 88.7% | 18.25% | 265299572.29 | -70.45% | Delay | 19.47% | 282994708.45 | 16.12% | 244200000 | 12.78% | 193600000 | 1.59 | 63.38
WIN/0084/25-26 | E15 Road | ADCL | HUDCO | BSR | LASA | Trunk Infra | Chintalaboyana Durga Prasad | MADHU THUMMALAPALLI | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 186.18 | 4.23 | 1940536887.35 | 84.38% | 30.11% | 560571943.77 | -54.27% | Delay | 30.43% | 566564159.96 | 26.06% | 505700000 | 22.74% | 441200000 | 5.66 | 49.13
WIN/0074/25-26 | N15 Road | ADCL | WB+ADB | NCC | Aarvee | Trunk Infra | PITCHUKA AJAYKUMAR | Ashok Yanikapati | Manchikalapati Vaasu Charan | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 331.16 | 3.32 | 3421553916.69 | 86.91% | 23.2% | 768284449.78 | -63.71% | Delay | 24.47% | 810512477.18 | 21.90% | 749200000 | 18.13% | 620200000 | 0 | 98.69
WIN/0070/25-26 | N12 Road | ADCL | WB+ADB | NCC | Aarvee | Trunk Infra | Vamsi Krishna Nadella | Veerababu Rokkam | Sridhar Sali | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 443.84 | 3.94 | 4613253122.94 | 83.18% | 16.92% | 750779580.34 | -66.27% | Delay | 17.24% | 765350628.99 | 13.73% | 633300000 | 12.27% | 566200000 | 0 | 93.6
WIN/0078/25-26 | N11 Road | ADCL | WB+ADB | RVR | Aarvee | Trunk Infra | Gopalam Jagadeesh | Dr. P Ganapati Naidu | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 273.13 | 3.48 | 2826370534.25 | 63.67% | 21.89% | 597878480.25 | -41.78% | Delay | 21.88% | 597580150.56 | 19.76% | 558600000 | 17.14% | 484300000 | 2.32 | 96.92
WIN/0060/25-26 | N9 Road | ADCL | WB+ADB | BSR | Aarvee | Trunk Infra | Mathi Ram Sunil | Rohit Kumar Muppavarapu | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 381.82 | 4.24 | 3980036382.52 | 95.55% | 35.48% | 1354537668.09 | -60.07% | Delay | 36.62% | 1398208970.43 | 33.13% | 1318500000 | 29.64% | 1179600000 | 1.41 | 150.15
WIN/0086/25-26 | N6 Utilities | ADCL | WB+ADB | MEIL | Aarvee | Trunk Infra | Gudiseva Sai Krishna | AKKIRAJU CHANDRASEKHAR | Manchikalapati Vaasu Charan | Ch.SRNV Ramesh | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 183.21 | 4.02 | 1905713471.14 | 92.12% | 37.99% | 696058045.25 | -54.13% | Delay | 38.05% | 697075010.39 | 34.32% | 654100000 | 27.58% | 525700000 | 0.64 | 182.75
WIN/0085/25-26 | E14 Road | ADCL | WB+ADB | MEIL | Aarvee | Trunk Infra | Bojjanapalli Naga Srikanth | MADHU THUMMALAPALLI | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 241.67 | 4.42 | 2523539087.80 | 58.2% | 22.64% | 547209919.12 | -35.55% | Delay | 22.66% | 547680713.52 | 18.32% | 462300000 | 16.81% | 424100000 | 0.65 | 104.97
WIN/0081/25-26 | E9 Road | ADCL | WB+ADB | RVR | Aarvee | Trunk Infra | Gopalam Jagadeesh | Dr. P Ganapati Naidu | Battula Sridhar | Kontham Rama Mohana Rao | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 419.96 | 3.84 | 4360916188.22 | 64.29% | 29.86% | 1254089092.64 | -34.43% | Delay | 30.08% | 1263177895.37 | 27.36% | 1193000000 | 20.35% | 887600000 | 1.92 | 198.43
WIN/0073/25-26 | E8 Road | ADCL | WB+ADB | RVR | Aarvee | Trunk Infra | Bojjanapalli Naga Srikanth | MADHU THUMMALAPALLI | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-04-2025 | 27-12-2026 | 27-04-2027 | 372.23 | 4.19 | 3878264755.92 | 64.25% | 39.4% | 1466592716.36 | -24.85% | Delay | 39.88% | 1484467395.68 | 34.19% | 1326000000 | 27.70% | 1074400000 | 5.13 | 211.55
WIN/0067/25-26 | E3 Road - Phase I | ADCL | WB+ADB | NCC | Aarvee | Trunk Infra | Vukoti Sivagangadhar Rao | Appaji Yandrapu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 28-04-2025 | 27-12-2026 | 27-04-2027 | 364.41 | 4.12 | 3794273529.00 | 88.21% | 25.09% | 914200776.02 | -63.12% | Delay | 26.04% | 949112764.6 | 15.35% | 582600000 | 13.14% | 498400000 | 1.09 | 242.92
WIN/0038/24-25 | Bungalows for Principal Secretaries & Secretaries | AGICL | HUDCO | KMV | Bureau Veritas | H&B Buildings | Pasam Mahendra, Ramesh Naidu Reddy, Mohan Krishna | Gurugubelli Appala Naidu | K Narayana Murthy | Nishat Mahammad | G Venkateswara Rao | 28-04-2025 | 30-11-2026 | 27-10-2026 | 411.38 | 4.34 | 4292336214.54 | 100% | 36.58% | 1504684392.03 | -63.42% | Delay | 37.97% | 1562050773.16 | 27.48% | 1179600000 | 18.98% | 814600000 | 0.17 | 34.1
WIN/0110/26-27 | Additional work of AIS Secretary & AIS Principal Secretary Bungalows | AGICL | HUDCO | KMV | Bureau Veritas | H&B Buildings | Pasam Mahendra, Ramesh Naidu Reddy, Mohan Krishna | Gurugubelli Appala Naidu | K Narayana Murthy | Nishat Mahammad | G Venkateswara Rao | 12-07-2026 | 08-01-2027 | 08-01-2027 | 90.48 | 4.89 | 949078802.96 | 40.33% | 7% | 63383177.34 | -33.33% | Delay | 7.12% | 64418057.7 | 6.42% | 60900000 | 7.34% | 69700000 | 0 | 0
WIN/0003/26-27 | Clubhouse Building (G+4) to AIS, Secretaries and Principal Secretaries | AGICL | Other Funds | NCC | NA | H&B Buildings |  | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 24-06-2026 | 23-12-2026 | 23-12-2026 | 43.98 | 3.82 | 456600000 | 0% | 0% | 0 | 0% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0 | 0
WIN/0173/26-27 | Construction of Additional Bungalows at Rayapudi Village | AGICL | Other Funds | KMV | Bureau Veritas | H&B Buildings | Pasam Mahendra | Gurugubelli Appala Naidu | K Narayana Murthy | D L Srinivas | G Venkateswara Rao | 14-08-2026 | 10-02-2027 | 10-02-2027 |  | 4.20 | 280656932.53 | 0% | 0% | 0 | 0% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0 | 0
WIN/0032/24-25 | Hon'ble MLAs and MLCs and AIS Officers - Housing | AGICL | WB+ADB | NCC | Bureau Veritas | H&B Buildings | Guttameda Vinod Kumar | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 28-04-2025 | 30-09-2026 | 27-10-2026 | 439.27 | 4.14 | 4523042209.90 | 100% | 83.23% | 3656231008.78 | -16.77% | Delay | 84% | 3689957114.74 | 76.07% | 3440500000 | 59.93% | 2710700000 | 0 | 15.22
WIN/0165/26-27 | Clubhouse Building (G+3) to Ho'ble MLAs and MLCs | AGICL | Other Funds | NCC | NA | H&B Buildings |  | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 24-06-2026 | 23-12-2026 | 23-12-2026 | 49.21 | 3.82 | 510900000 | 0% | 0% | 0 | 0% | Delay | 0% | 0 | 0.00% | 0 | 0.00% | 0 | 0 | 0
WIN/0043/24-25 | Assembly - Structure | AGICL | HUDCO | L&T | TUV | H&B Offices | Thulisa Naik Vadithe | KVS Pavan Kumar | Ganasyam | Nishat Mahammad | Addagada Venkateswara Rao | 27-05-2025 | 26-05-2027 | 26-05-2027 | 590.87 | 4.48 | 6173370035.73 | 69.39% | 16.48% | 973871500 | -52.91% | Delay | 17.04% | 1006711214.74 | 14.26% | 880300000 | 10.73% | 662300000 | 0 | 71.31
WIN/0044/24-25 | High Court | AGICL | HUDCO | NCC | TUV | H&B Offices | K Mahesh Kumar | KVS Pavan Kumar | GVSD Hima Bindu | G Dhana Lakshmi | Punnam V K Bhaskar | 21-06-2025 | 20-06-2027 | 20-06-2027 | 751.12 | 4.52 | 7860557470.95 | 59.07% | 26.1% | 1960279852.78 | -32.97% | Delay | 26.29% | 1974878207.4 | 21.80% | 1713600000 | 16.34% | 1284600000 | 0 | 53.15
WIN/0074/24-25 | Project Office | AGICL | HUDCO | KPC | Feedback | H&B Offices | Noonsavathu Krishna Kumar Naik | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 12-02-2024 | 30-10-2025 | 30-10-2025 | 135.98 | 4.84 | 1359770792.17 | 100% | 100% | 1359800000 | 0% | Completed | 100% | 1359800000 | 94.35% | 1283000000 | 28.22% | 383700000 | 0 | 4.41
WIN/0134/25-26 | Bungalows for Hon'ble Ministers & Hon'ble Judges | AGICL | HUDCO | BSR | Bureau Veritas | H&B Buildings | Manupoti Tirumala Krishna | Gurugubelli Appala Naidu | K Narayana Murthy | Nishat Mahammad | G Venkateswara Rao | 28-04-2025 | 30-09-2026 | 27-10-2026 | 401.37 | 4.41 | 4190727369.90 | 99.62% | 57.51% | 2308257635.45 | -42.11% | Delay | 60.83% | 2441661282.97 | 54.30% | 2275800000 | 47.07% | 1972700000 | 0 | 120.48
WIN/0106/25-26 | E13 Road - Extn. upto NH-16 | ADCL | Other Funds | MEIL | Voyants | Trunk Infra | Mathi Ram Sunil | Rohit Kumar Muppavarapu | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-07-2025 | 27-03-2027 | 27-07-2027 | 290.44 | 4.10 | 3033301681.12 | 34.73% | 6.7% | 194473890.92 | -28.04% | Delay | 6.71% | 194885255.59 | 3.63% | 145200000 | 3.67% | 147100000 | 0 | 54.25
WIN/0105/25-26 | E15 Road - Extn. upto NH-16 | ADCL | Other Funds | MEIL | Voyants | Trunk Infra | Chintalaboyana Durga Prasad | MADHU THUMMALAPALLI | V Padmakar’s prasad | Veturi Srinivas | Narasimha Murthy B | 28-07-2025 | 26-01-2027 |  | 21.03 | 3.98 | 218670380.77 | 100% | 35.24% | 74111412.77 | -64.76% | Delay | 35.48% | 74616101.23 | 7.35% | 53500000 | 3.09% | 22500000 | 0 | 35.71
WIN/0139/25-26 | 3 PEB structures near Project Office | AGICL | Other Funds | NCC | NA | H&B Offices | Guttameda Vinod Kumar | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 22-05-2025 | 21-09-2025 | 21-09-2025 | 28.69 | 4.23 | 286903330.47 | 100% | 100% | 286900000 | 0% | Completed | 100% | 286900000 | 99.64% | 285900000 | 100.00% | 340900000 | 0 | 2.92
WIN/0108/25-26 | Water Distribution Centres (WDCs) | ADCL | WB+ADB | NCC | LASA | Water Supply | Juluri Naga Raja Kumar | Appaji Yandrapu | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 27-09-2025 | 26-05-2027 | 28-08-2027 | 376.81 | 4.28 | 3768060762.25 | 17.49% | 5.96% | 224618093.53 | -11.53% | Delay | 6.07% | 228837336.23 | 5.54% | 208900000 | 5.60% | 211100000 | 9.2 | 84.03
WIN/0107/25-26 | Water Treatment Plant (WTP) | ADCL | WB+ADB | NCC | LASA | Water Supply | K Omprakash | Yandrapu Appaji | Maditati Sridhar Reddy | Tirumalasetty Vykunta Rao | Tumeti Moses Kumar | 27-09-2025 | 26-05-2027 | 28-08-2027 | 411.54 | 4.29 | 4115387679.73 | 48.26% | 22.21% | 913887427.28 | -26.05% | Delay | 22.5% | 926159557.77 | 22.31% | 918100000 | 18.38% | 756200000 | 0 | 100.57
WIN/0008/25-26 | Jungle Clearance | ADCL | Other Funds | NCC | - | LPS Infra |  |  |  | R Hanumantha Reddy | Ch Dhanunjaya | 28-08-2024 | 27-09-2024 | 27-09-2024 | 31.95 | 3.70 | 319502364.30 | 100% | 100% | 308102569.24 | 0% | Completed | 100% | 308102569.24 | 0.00% | 0 | 0.00% | 0 | 0 | 0
WIN/0163/25-26 | MEP for 3 PEB Structures | AGICL | Other Funds | NCC | - | H&B Offices | Guttameda Vinod Kumar | Gurugubelli Appala Naidu | Paidi Vinodh Kumar | Bitra Srinivasa Rao | Punnam V K Bhaskar | 04-09-2025 | 03-01-2026 | 03-01-2026 | 40.36 | 4.34 | 403599575.23 | 100% | 100% | 403600000 | 0% | Completed | 100% | 403600000 | 78.08% | 315100000 | 61.29% | 247400000 | 0 | 2.92
WIN/0113/25-26 | AGC Infrastructure | AGICL | Other Funds | MEIL | Tractebel | H&B Offices | Gummadi Nagoor Babu | Marreddy Hemambaradhara Reddy | MV Vidya Sagar |  | Addagada Venkateswara Rao | 21-11-2025 | 20-11-2027 | 20-11-2027 | 682.27 | 4.55 | 7133124433.73 | 41.01% | 5.39% | 367669525.93 | -35.62% | Delay | 5.73% | 390698552.07 | 3.19% | 227600000 | 1.54% | 110100000 | 3.59 | 271.54
WIN/0069/25-26 | 220KV EHV lines rerouting | APTRANSCO | NABARD | BSR | - | Electrical Infra | Fayazuddin Varaparla | Vss Hanumantha Rao | Lakshmi Narayana Gadde | Yedidhi S R K V V L Narasimha Rao | G Venkateswara Rao | 08-01-2025 | 31-07-2027 | 31-07-2027 | 978.93 | 8.98 | 10824411437.00 | 44.91% | 43.73% | 4280712872.86 | -1.19% | Delay | 45.09% | 4413650172.26 | 38.12% | 4126000000 | 28.18% | 3050000000 | 0 | 0
WIN/0068/25-26 | 400KV DC lines rerouting | APTRANSCO | NABARD | PVR & KRRTPPL | - | Electrical Infra | Fayazuddin Varaparla | Vss Hanumantha Rao | Lakshmi Narayana Gadde | Yedidhi S R K V V L Narasimha Rao | G Venkateswara Rao | 09-04-2025 | 08-10-2026 | 08-10-2026 | 395.84 | 8.99 | 3900600000.00 | 90% | 63.19% | 2501323518.9 | -26.81% | Delay | 64.53% | 2554293783.99 | 51.80% | 2020500000 | 0.00% | 0 | 0 | 0
Total | [16 empty] | 423988499707.9601 | 59.42% | 23.72% | 96824159697.26 | -35.7% |  | 24.32% | 99294859434.53 | 20.33% | 86282100000 | 16.58% | 70391800000 | 371.84 | 12581.72